## query (4)
Business Unit | Division | Project Name | PM | PMR Date | Risk Metric | Risk Mgmt | Journal Metric | Customer Feedback? | Plan Metric | Plan Status | Deliverables Metric | Deliverable Notes | QA Metric | QA Notes | CM Metric | Gen'l PM/Site Status Metric | Notes | Closeout Date | Item Type | Path
Civil Programs | Civil Programs | ADS-B (Rel 1) | Shelli Debardi |  | No (R) | Last risk logged 6 months ago; not closed or mitigate | Inconsistent (Y) | Feedback reported in April in the Journal, but no evidence of discussion in PMRs | In Progress (Y) | Plan still in draft | No (R) | Deliverables not uploaded since 2015; document library has unrelated items | Red | No QA approvals since 2015 | Inconsistent (Y) | Yellow | Project site needs updates and completion of Plan. Ensure QA Log is used and risks are current |  | Item | myProjects/Lists/Project Management Metrics
Civil Programs | Civil Programs | Advanced Technology Development & Prototyping | Robert Manuse | 11/27/2017 | Inconsistent (Y) | 9/2017 risks not closed or mitigated | Yes (G) |  | Completed/Not Approved (Y) |  | Yes (G) |  | Some, but not consistent (Y) | Need Plan approval | Yes (G) | Green |  |  | Item | myProjects/Lists/Project Management Metrics
Civil Programs | Civil Programs | ASR-11 | Lee Smith | 3/31/2016 | No (R) |  | No (R) |  | Needs Update (Y) |  | No (R) |  | No (R) |  | N/A | Red | No activity on this site | 12/15/2017 | Item | myProjects/Lists/Project Management Metrics
Civil Programs | Civil Programs | ASR-9 | Kelly Pashkoff |  | Inconsistent (Y) | Looks like a recent risk was added, but it's not dated by year | No (R) | There is no customer feedback indicated in the Journal, but recent issues are added. | In Progress (Y) | Assumed that it is checked out because no documents show in the Library | No (R) | No deliverables uploaded in 2017 | Red | PMR indicates that QA is expected, but there are no entries in this log | Inconsistent (Y) | Yellow | Check that documents are checked in. Good that PMRs are being done |  | Item | myProjects/Lists/Project Management Metrics
Civil Programs | Civil Programs | ATS Support | Robert Manuse | 11/27/2017 | Inconsistent (Y) | Mitigation/dates not shown | Yes (G) |  | Needs Update (Y) |  | No (R) | No deliverables uploaded since 2015 | Some, but not consistent (Y) | No QA since 2015; need Plan QA | Yes (G) | Yellow |  |  | Item | myProjects/Lists/Project Management Metrics
Civil Programs | Civil Programs | Engility Group 1 | Samuel Ekhaus |  | Yes (G) |  | Yes (G) |  | Approved (G) |  | N/A, exception noted in plan |  | Plan only, exception for deliverables noted (G) |  | Yes (G) | Green |  |  | Item | myProjects/Lists/Project Management Metrics
Civil Programs | Civil Programs | ETASS/HSI Weather Programs Support | Troy Hammond | 4/5/2017 | Inconsistent (Y) |  | Inconsistent (Y) |  | Needs Update (Y) |  | No (R) |  | No (R) |  | Inconsistent (Y) | Red | No site activity since April 2017 |  | Item | myProjects/Lists/Project Management Metrics
Civil Programs | Civil Programs | ISAM/SSMT | Robert Blumer | 12/1/2017 | Yes (G) |  | Yes (G) |  | Needs Update (Y) |  | No (R) | No deliverables since 2015 | No (R) |  | Yes (G) | Yellow | Needs update |  | Item | myProjects/Lists/Project Management Metrics
Civil Programs | Civil Programs | NASA ATD-2 | Benjamin Levy |  | Yes (G) | Two recent risks added, with resolution dates | Yes (G) | Journal is being used consistently; no direct customer feedback yet | Completed/Not Approved (Y) | Plan has been worked; approval in the QA log is needed | Yes (G) |  | Some, but not consistent (Y) | Plan approval needs to be documented | Yes (G) | Green | Effort to get this site updated is good. |  | Item | myProjects/Lists/Project Management Metrics
Civil Programs | Civil Programs | SE2025 Veracity – EVM Focal Point | Sean Osborne |  | Yes (G) | Recent risks mitigated? | Yes (G) |  | Not Started (R) |  | No (R) |  | No (R) |  | Inconsistent (Y) | Red | No Plan; no PMRs noted |  | Item | myProjects/Lists/Project Management Metrics
Civil Programs | Civil Programs | Terminal Facilities (AJW) | Alan Wilson | 12/7/2017 | Yes (G) |  | Yes (G) |  | Completed/Not Approved (Y) |  | Some, but not consistent (Y) | No deliverables since March 2017 | No (R) | Need Plan approval | Yes (G) | Yellow |  |  | Item | myProjects/Lists/Project Management Metrics
Civil Programs | Civil Programs | Veracity eFast EVM | Sean Osborne | 9/29/2017 | [11 empty] | Yellow | Site not up-to-date | 12/13/2017 | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Central Region | Agile Combat Support - HX5 | Howard Packer |  | Inconsistent (Y) | Risks have not been updated; it appears loss of personnel is a big risk | Inconsistent (Y) | Journal is being used, but it appears that issues and customer feedback should be more featured. | Approved/Not Compliant (Y) | Updated this year; needs links to org level plans | Some, but not consistent (Y) | Only two MSRs for this year are uploaded | Yellow | Plan is approved through the QA Log, but nothing else. | Yes (G) | Yellow | Need to identify and track risks as they become issues; close as appropriate |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Central Region | DS TAT AFIT | Howard Packer | 11/30/2017 | No (R) |  | Inconsistent (Y) |  | Approved/Not Compliant (Y) | Updated this year; needs links to org level plans | Yes (G) |  | Some, but not consistent (Y) | Plan is approved, but not deliverables. Is there an exception? | Yes (G) | Yellow | Need to consider risks and keep Journal current |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Central Region | DS TAT AFLCMC/EZ | Howard Packer | 11/30/2017 | No (R) |  | Inconsistent (Y) |  | Approved/Not Compliant (Y) | Updated this year; needs links to org level plans | Yes (G) |  | Some, but not consistent (Y) | Plan is approved, but not deliverables. Is there an exception? | Yes (G) | Yellow | Need to consider risks and keep Journal current |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Central Region | DSTAT C-130j CARD | Peter Meisl | 11/30/2017 | No (R) |  | Inconsistent (Y) | Only 1 item in 2017 | Not Started (R) |  | No (R) |  | No (R) |  | Inconsistent (Y) | Red | Little implementation effort |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Central Region | DSTAT C-5 | Howard Packer | 11/30/2017 | No (R) |  | Inconsistent (Y) |  | Not Started (R) |  | No (R) |  | No (R) |  | N/A | Red | Need a plan |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Central Region | EPASS B2 | Howard Packer | 11/30/2017 | Inconsistent (Y) | None since Feb; not mitigated or closed | Inconsistent (Y) |  | Approved/Not Compliant (Y) | Updated this year; needs links to org level plans |  |  | Some, but not consistent (Y) | Plan is approved, but not deliverables. Is there an exception? | Yes (G) | Yellow |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Central Region | EPASS Fighter-Bomber | Howard Packer | 11/30/2017 | No (R) |  | Inconsistent (Y) |  | Completed/Not Approved (Y) | vers. .5; needs QA review with org plans | Yes (G) |  | Some, but not consistent (Y) | Need plan review and deliverables. Is there an exception? | Yes (G) | Yellow | Make sure risks and issues are communicated |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Central Region | EPASS HQ AFMC/A4 | Michael Brown | 11/30/2017 | No (R) | Turnover is a BIG risk | No (R) | Turnover is a an issue; no journal items in 2017 | Not Started (R) |  | No (R) | No deliverables uploaded since April | No (R) |  | Inconsistent (Y) | Red | No project data or plan |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Central Region | EPASS: CRH | Howard Packer | 11/30/2017 | No (R) | Turnover is a BIG risk | Inconsistent (Y) | Only 1 item since April; isn't turnover an issue? | Approved (G) | Plan needs to be checked in. Are the new org level plans linked? | Yes (G) |  | Yes (G) | Plan is reviewed, but not deliverables. Exception noted in Plan? | Yes (G) | Yellow | Extra scrutiny as an appraisal project. Need to focus on communicating risks and issues |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Central Region | ISR Sensors - DCS | Glen Fike | 11/30/2017 | Inconsistent (Y) | Turnover is a BIG risk | Inconsistent (Y) | Focus on issues and customer feedback | Approved (G) | Plan needs to be checked in. Are the new org level plans linked? | Yes (G) |  | Yes (G) | Plan is reviewed, but not deliverables. Exception noted in Plan? | Yes (G) | Yellow | Focus on communicating risks and issues; clarify who reviews deliverables |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Central Region | NAPMA Cost Sppt (Windmill) | Peter Meisl | 11/30/2017 | No (R) |  | Inconsistent (Y) | Only 1 item in 2017; big ISSUE that the project loses money | Needs Update (Y) |  | Yes (G) |  | No (R) |  | Yes (G) | Yellow | Project ends in Jan 2018. |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense National Capitol Region | NavAir 4.2 NSI | Christina Snyder | 12/8/2017 | Yes (G) |  | Inconsistent (Y) |  | Approved (G) |  | No (R) | No deliverables uploaded since May 2016 | Some, but not consistent (Y) | Plan QA, but not for deliverables | Yes (G) | Yellow | Need to upload and review deliverabbles |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense National Capitol Region | NAVAIR PMA 202 Support | Christina Snyder | [14 empty] | 12/1/2017 | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense National Capitol Region | ONR 03TTX | Joseph Piff | 12/8/2017 | Inconsistent (Y) | No risks in the last 6 months? | Yes (G) |  | Approved (G) | Were new org level plans added? | Yes (G) |  | Yes (G) |  | Yes (G) | Green |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense National Capitol Region | ONR SBIR/STTR Support | Joseph Piff | 12/8/2017 | Inconsistent (Y) | No risks since April? | Inconsistent (Y) |  | Approved (G) | Were new org level plans added? | Yes (G) |  | Yes (G) |  | Yes (G) | Green |  |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense National Capitol Region | ONRG (London) Support | Joseph Piff | 12/8/2017 | Inconsistent (Y) |  | Inconsistent (Y) | No items since March? | Approved (G) | Were new org level plans added? | Yes (G) |  | Yes (G) |  | Yes (G) | Green | Make sure Plan is current & approved |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense National Capitol Region | PEO EIS - CSA Subcontract | Joseph Piff | 12/8/2017 | No (R) |  | Inconsistent (Y) | No items since August | Needs Update (Y) | Were new org level plans added? | Yes (G) |  | Yes (G) | Updated Plan should get QA approval | Yes (G) | Yellow | Make sure Plan is current & approved |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Southeast Region | AED Fixed Wing | Nathaniel Whitfield | 12/1/2017 | Yes (G) | Keep adding | Yes (G) |  | Needs Update (Y) | Update links; check currency since 2015 | Yes (G) |  | Plan only, exception for deliverables noted (G) | Do updated plan review | Yes (G) | Green | Needs plan review to stay green |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Southeast Region | ANMP | Ed Myszka | 11/30/2017 | No (R) | Protest is a risk | Inconsistent (Y) |  | In Progress (Y) | Updated sub-plans; update the rest when protest is resolved | Yes (G) |  | No (R) | Need updated plan approval | Yes (G) | Yellow | Update when protest is resolve |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Southeast Region | Apache AED | Laura Bequette | 11/27/2017 | No (R) |  | Yes (G) |  | Completed/Not Approved (Y) |  | Yes (G) |  | No (R) | Need QA review for Plan | Yes (G) | Green | Make sure risks are considered |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Southeast Region | FW Log | James Gaddis | [14 empty] | 12/2017 | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Southeast Region | JSIL II | James Gaddis | 12/1/2017 | Inconsistent (Y) |  | Inconsistent (Y) |  | Approved (G) |  | Yes (G) |  | Some, but not consistent (Y) |  | Yes (G) | Green | Project will close at year-end |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Southeast Region | PM ASE II |  | 11/30/2017 | [12 empty] | No activity on this project since August 2016; new PM has not been named |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Southeast Region | PM Fixed Wing II | Craig Zgraggen | 11/2/2017 | Inconsistent (Y) | Only 1 risk added in 6 months | Yes (G) |  | Needs Update (Y) | Add new sub-plan links; update | Some, but not consistent (Y) |  | Some, but not consistent (Y) |  | Yes (G) | Yellow | Some polishing needed before the appraisal |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Southeast Region | PM UAS | Robert Hess | 11/29/2017 | Inconsistent (Y) | No current risks | Yes (G) |  | Needs Update (Y) | Update when status is determined | Some, but not consistent (Y) |  | No (R) | Not since 2015 | Yes (G) | Yellow | Update when ongoing status is determined |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Defense Southeast Region | TACT | Scott Brown |  | No (R) |  | Inconsistent (Y) |  | Not Progressing (R) |  | Some, but not consistent (Y) | No deliverables uploaded in 2017 | No (R) |  | Yes (G) | Red | Not much site documentation |  | Item | myProjects/Lists/Project Management Metrics
MCR Global | Global NATO Programs | BI-SC PMC | Andrew Dreslinski | 11/2/2017 | No (R) |  | No (R) |  | In Progress (Y) | 5 plan versions; consolidate? PM needs to complete | No (R) |  | No (R) |  | Yes (G) | Red |  |  | Item | myProjects/Lists/Project Management Metrics
MCR Global | Global NATO Programs | MODSIMMET | Gary Horne |  | No (R) |  | No (R) |  | Not Started (R) |  | No (R) |  | No (R) |  | N/A | Red | No site use yet |  | Item | myProjects/Lists/Project Management Metrics
MCR Global | Global NATO Programs | NACMA | Joseph Helfter | 11/2/2017 | No (R) |  | No (R) |  | Completed/Not Approved (Y) | Were new org level plans added? | No (R) |  | Some, but not consistent (Y) | Plan not yet approved | Inconsistent (Y) | Red | Little site use - where are the PMRS? |  | Item | myProjects/Lists/Project Management Metrics
MCR Global | Global NATO Programs | NAGSMA | Paul Torilli |  | No (R) |  | No (R) | [11 empty] | Item | myProjects/Lists/Project Management Metrics
MCR Global | Global NATO Programs | NCIA SSC3 | Donovan Pavlik | 11/2/2017 | No (R) |  | No (R) |  | In Progress (Y) | 2 plans in the library - one is checked out, but not by the PM | No (R) |  | No (R) |  | Inconsistent (Y) | Red | Project under review for appraisal |  | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | AICIG Bridge | Kevin Sievers | [15 empty] | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | DMDPO | Pat Kelly | [15 empty] | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | EPASS | Elia Sanjume | [15 empty] | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | E-SMARTS-BAH | Pat Kelly | [15 empty] | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | LANDMARK PS | Pat Kelly | [15 empty] | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | MACSS TO 002 | Elia Sanjume | [15 empty] | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | NELO CAED Support | Paul Dash | [15 empty] | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | NELO/ONI AMOD | Paul Dash | [15 empty] | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | R2-3G/PM EW | Dave Peters | [15 empty] | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | RICE | Pat Kelly | [15 empty] | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | RICE Bridge | Pat Kelly | [15 empty] | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | Smartronix CEA | Pat Kelly | [15 empty] | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | Support to CCOS | Pat Kelly | [15 empty] | Item | myProjects/Lists/Project Management Metrics
Defense Programs | Intelligence Programs | TRADOC G2 Core | Pat Kelly | [15 empty] | Item | myProjects/Lists/Project Management Metrics
Space Programs | Space Programs | JNWC | Christina Sharp | 11/27/2017 | No (R) |  | No (R) |  | Needs Update (Y) |  | Some, but not consistent (Y) | Only 1 2017 PMR | No (R) | No QA since 2014 | Yes (G) | Yellow | Good job on small project |  | Item | myProjects/Lists/Project Management Metrics
Space Programs | Space Programs | LLNL Integrated Project Management Development | Christopher Seemann | 11/28/2017 | No (R) |  | No (R) |  | Not Started (R) |  | No (R) |  | No (R) |  | No (R) | Red | Very little site use |  | Item | myProjects/Lists/Project Management Metrics
Space Programs | Space Programs | MILSATCOM MC01 | Mariza Corral | 11/20/2017 | Yes (G) |  | Yes (G) | Exceptional ratings from the customer!! | Completed/Not Approved (Y) | Are updates complete? | Yes (G) | Make sure deliverables are uploaded as they are completed | Some, but not consistent (Y) | Jesse needs to approve; need QA for deliverables | Inconsistent (Y) | Green | Needs some improvement in QA |  | Item | myProjects/Lists/Project Management Metrics
Space Programs | Space Programs | MILSATCOM MC03 Admin Support | Daniel Belden | 11/20/2017 | Inconsistent (Y) | No risks added in 2017 | Yes (G) |  | Needs Update (Y) | Subplans were added, but not general update | No (R) |  | Yes (G) |  | Yes (G) | Yellow | Not clear if the plan has been updated and reviewed |  | Item | myProjects/Lists/Project Management Metrics
Space Programs | Space Programs | OASIS SATCOM | Robert Romero | 11/27/2017 | No (R) |  | Yes (G) |  | Needs Update (Y) |  | Some, but not consistent (Y) | No deliverables in 2017, but QA happened | Yes (G) | Need overall plan approval | Yes (G) | Yellow | Need plan review and consideration of risks |  | Item | myProjects/Lists/Project Management Metrics
Space Programs | Space Programs | SNL Nuclear Weapons Project Support | Christopher Seemann | 11/20/2017 | No (R) |  | No (R) |  | Not Started (R) |  | No (R) |  | No (R) |  | N/A | Red | Very little site use |  | Item | myProjects/Lists/Project Management Metrics