## RiskTable
RiskId | Desc | Details | Rating | Score | Likelihood | Technical | Schedule | Cost | Status | Date | Owner | Org
3803 | TECH OP RISK: | Receiver Protector: Limited Life Expectancy and Potential Outages | High | 23 | C | 5 | NIL | NIL | Pending | 2017-06-26 | Pamela Maxwell
3198 | DRSR: | Sites with Unapproved Modified Remote SCIP and Increased Program Cost | Mediam | 13 | E | 2 | NIL | NIL | Approved | 2016-08-10 | Pamela Maxwell
3575 | DRSR: | Risk 3575: DRSR: Sites with Unapproved Modified Remote SCIP and Potential Missed APB Milestone | High | 23 | C | 5 | NIL | NIL | Approved | 2017-03-03 | Fred Perry
2965 | TECH OP RISK: | DCE: Racal-Milgo Modem Depot Exhaustion and Potential Loss of Service | Low | 10 | A | 4 | NIL | NIL | Approved | 2017-03-14 | Lynn Garst
3564 | TECH OP RISK: | A/D Converter: Lack of A/D Converter Supportability and Potential Loss of Redundancy | Mediam | 18 | A | 5 | NIL | NIL | Pending | 2017-03-14 | Lynn Garst
3671 | NA | Outdated Site Infrastructure and Potential Service Disturbance | Low | 9 | B | 2 | NIL | 3 | Approved | 2017-05-25 | Pamela Maxwell
2847 | DRSR: | Sites with Bandwidth Manager and Potential Missed APB Milestone | High | 24 | D | 5 | NIL | NIL | Approved | 2016-05-04 | Fred Perry
3675 | DRSR: | ASIS II Card Procurement Delay and Potential Missed APB Milestone | Low | 7 | B | 2 | NIL | NIL | Pending | 2017-04-11 | Fred Perry
3749 | DRSR: | Sites with Bandwidth Manager and Potential Increase to Program Cost | Mediam | 14 | C | NIL | NIL | 3 | Pending | 2017-05-10 | Fred Perry

## SiteTable
RiskId | Location
2965 | Chicago IL
2965 | Denver CO
2965 | Miramar CA
2847 | Philadelphia PA
2847 | Andrews AFB MD
2847 | -Baltimore, MD (BWI)
2847 | Chantilly VA
2847 | Charlottesville VA
2847 | Harrisburg PA
2847 | Martinsburg WV
2847 | Richmond VA
2847 | Washington National VA
2847 | Boston MA
2847 | Manchester NH
3675 | Las Angeles
3675 | Atlanta GA
3675 | Westbury NY
3749 | Philadelphia PA
3749 | Andrews AFB MD
3749 | Baltimore MD
3749 | Chantilly VA
3749 | Charlottesville VA
3749 | Harrisburg PA
3749 | Martinsburg WV
3749 | Richmond VA
3749 | Washington National VA
3749 | Boston MA
3749 | Manchester NH